## High Level Project Timeline
NM Tiger Team - Clinical Trial App - High Level Target Dates (draft)
| 2020-08-01 | 2020-09-06 | 2020-10-06 | 2020-11-06 | 2020-12-06 | 2021-01-07 | 2021-02-07 | 2021-03-07 | 2021-04-07 | 2021-05-07 | 2021-06-07 | 2021-07-07
Project Kickoff
Design Tab
Business Requirements
Development
BCH Demos
User Testing
Home Tab
Business Requirements
Development
BCH Demos
User Testing
Help Tab
Business Requirements
Development
BCH Demos
User Testing
Trial Conduct Tab
Business Requirements
Development
BCH Demos
User Testing
Demo an actual want the tab to do - Clement - first thing in the business requirements
Project Activities
Change Management Activities
Paper publication
BCH Pre-Implementation Activities
Project Publication/Project Checkout
Transition Documentation
Project post - implementation monitoring and feedback
Project transitions to BCH
Note on Y13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: User testing will be combined with the home/help tab.
Note on AK22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This work represents updates for the trial conduct tab once development is finished.
Note on AJ32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Revisit the home and help tab for an updates.
Note on B38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: BCH promotion and communication plan. Identify test group of researchers to provide feedback. Should we have potentially joint press release. Reply: Still want to complete this change management activities. This becomes NM corporate communication and Foundation. Will need communication to BCH communication team.
Note on B40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: BCH has to create a shiny app/github and then need to publish - pre-implementation activities
Note on B42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How do we integrate code and scalable from other external clinicals? How does that proces work?

## Detailed Project Timeline
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Legend title is in cell I1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | PROJECT TITLE | [5 empty] | Legend:
Enter Company Name in cell B2. A legend is in cells I2 through AC2. | Company Name | [5 empty] | On Track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell F3 or allow the sample formula to find the smallest date value from the Gantt Data table. Project Start Date: label is in cell D3. | Project Lead |  | Project Start Date: |  | 2020-08-18
A Scrolling Increment is in cell F4. Months for the dates in row 5 are displayed starting in cells I4 through cell BL4. Do not modify these cells. They are auto updated based on the project start date in cell F3. |  |  | Scrolling Increment: |  | 130 |  | December | [6 empty] | January | [34 empty] | February
Cells I5 through BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated. Do not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2020-12-26 to 2021-02-19
A scrollbar is in cells I6 through BL6. The increment for paging through the data is defined as 2 pages at a time and can be configured in the settings for the control bar. To jump forward or backward in the timeline, enter a value of 0 or higher in cell F4. A value of 0 takes you to the beginning of the chart.
This row contains headers for the project schedule that follows below them. Navigate from B7 through BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues through cell BL7. All project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table. | Milestone Description | Category | Assigned To | Progress | Start | No. Days | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | Design tab
| Business Requirements | Low Risk | Stan Crane/Clement Ma/Wendy London | 100% | 2020-10-01 | 100
| Development | Low Risk | Ben Garski/Danielle Pankey | 90% | 2020-10-15 | 90
| BCH Demos | Low Risk | Ben Garski/Danielle Pankey | 80% | 2020-11-01 | 90
| User Testing | Milestone | Clement Ma/Wendy London/Lori Kiraly/Susan Stegman | 0% | 2021-01-31 | 15 | bar: S to S
| Complete | Goal | Ben Garski | 0% | 2021-02-15 | 1 | M: 2
Conduct tab
| Business Requirements | Goal | Stan Crane/Clement Ma/Wendy London | 0% | 2021-02-28 | 30
| Development | Goal | Danielle Pankey/Lori Kiraly | 0% | 2021-03-31 | 30
| BCH Demos | Goal | Danielle Pankey/Lori Kiraly | 0% | 2021-04-15 | 15
| User Testing | Goal | Clement Ma/Wendy London/Lori Kiraly/Susan Stegman |  | 2021-04-30 | 15
| Complete | Milestone | Danielle Pankey/Lori Kiraly |  | 2021-05-15 | 1
Home tab
| Business Requirements | Goal | Stan Crane/Clement Ma/Wendy London | 50% | 2021-01-19 | 30 | T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2
| Development | Goal | Stan Crane |  | 2021-02-15 | 30 | M: 2; T: 2; W: 2; T: 2; F: 2
| BCH Demos | Goal | Stan Crane |  | 2021-03-15 | 14
| User Testing | Goal | Clement Ma/Wendy London/Lori Kiraly/Susan Stegman |  | 2021-03-15 | 14
| Complete | Milestone | Stan Crane |  | 2021-03-31 | 1
Help tab
| Business Requirements |  | Stan Crane/Clement Ma/Wendy London | 90% | 2021-01-19 | 30
| Development |  | Stan Crane | 0% | 2021-02-15 | 30
| BCH Demos | Milestone | Stan Crane | 0% | 2021-03-15 | 14
| User Testing |  | Clement Ma/Wendy London/Lori Kiraly/Susan Stegman | 0% | 2021-03-15 | 14
| Complete |  | Stan Crane | 0% | 2021-03-31 | 1
Project Activities
| Project implementation | Milestone | All |  | 2021-06-15 | 15
| Change management activities | Milestone | Clement Ma/Wendy London/Judy Berdan/Lori Kiraly |  | 2021-03-01 | 120
| Paper Publication | Goal | Clement Ma/Wendy London |  | 2021-03-01 | 110
| BCH Pre-implementation activities | Milestone | Clement Ma/Wendy London |  | 2021-04-01 | 60
| Transition Documentation | Goal | Stan Crane/Danielle Pankey |  | 2021-06-30 | 15
| Project implementation monitoring and feedback | Milestone | Clement Ma/Wendy London/Lori Kiraly/Judy Berdan |  | 2021-07-30 | 31
| Project transitioned to BCH | Milestone | Clement Ma/Wendy London/Lori Kiraly/Judy Berdan |  | 2021-08-02 | 1
This is an empty row
This row marks the end of the Gantt milestone data. DO NOT enter anything in this row. To add more items, insert new rows above this one. | To add more data, Insert new rows ABOVE this one
Note on B15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This includes testing happing once development finishes so it's it will be 2 1/2 months to complete tab.

## About
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks description, select a category of Goal, Milestone, On Track, Low Risk, Med Risk, High Risk, Progress as a percent of task completion, a Start Date and Number of days to complete the task. The Gantt chart fills in and is color coded to help distinguish the various categories. A scroll bar allows you to scroll through the timeline. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. Gantt Chart About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
This is the last instruction in this worksheet.