## Project Issues
Project Issues
Issue # | Issue Name | Description | Update | Temporary Workaround | Identified By | Date Identified | Date Resolved | Priority H/M/L

## Questions
SECURE Act & CARES Act 2020
Question list
Ref. ID | Date Logged | Status | Question | Priority | Identified By: | Issue Assigned To | Date Completed | Question Description | Resolution Description | Comments/Next Steps
1 | 2020-08-03 | Closed | Are there two different projects that Boston needs help with? | High | Ben | Ben | 2020-08-18 | Is one project to make packets and publish them or only making packets? | The goal is to create the online app and online packet. The focus of the partnership is focusing on the app is to be completed it would be wonderful.
2 | 2020-08-04 | Closed | Does the shiny dashboard depend on publishing an R library for others to use? (is this 1 or 2 projects) | Medium | Ben | Ben | 2020-08-18 |  | The function is written so we would just be putting into r shiny. This is the scope of the effort is creating the GUI.
3 | 2020-08-04 | Open | How are we deploying this? (shinyapps.io with an existing account?)/Deploying it for anyone to view? | Medium | Ben | Ben |  |  |  | 8/18/20: Wendy/Clement would like to understand the pros/cons of cloud based versus server based options including costs.
4 | 2020-08-18 | Open | Is there a non-profit cost for r shiny? | Medium | Wendy/Clement | Ben
5 | 2020-10-27 | Open | Is there a specific file that needs to be uploaded for the DLT data | Medium | Danielle
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22

## Topics
Item # | Topic or Issue | Start Date | Comments | Action steps required | Action Step Completion date | Type of product | Phase of Project | Topic or Issue Completion date

## Operational Decisions
Item # | Topic or Issue | Start Date | Comments | Action steps required | Action Step Completion date | Decision Makers | Type of product | Phase of Project | Topic or Issue Completion date
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Does this label make sense? Meeting attendees? Communicated to?

## Action Items
Action Plan
Use this template to capture outstanding items related to the rollout - smaller actions that needed to be taken that aren't already captured on the CM plan and risks & issues.
# | Action, Risk, Issue | Item | Owner | Due | Start | End | Status | Notes
1 | Action | Determine if Boston/Dana Farber have any intelliectual property considerations that we need to consider when designing the app and making it accessible worldwide to clinicians. | Clement Ma/Wendy London | 2020-08-31 | 2020-08-19 | 2020-08-31 | In progress | 8/31/20: Table discussion between Wendy/Clement. Inquiry about the precedent with sharing with others.
2 | Action | Does Boston/Dana Farber have an existing enterprise R shiny account? | Clement Ma/Wendy London | 2020-08-31 | 2020-08-19 | 2020-08-31 | Complete | 8/31/20: No enterprise account for r shiny but they do have one for both r studio and aws.
3 | Action | Purpose of the app is to be available as open source code to clinicials worldwide but this needs to be confirmed. | Clement Ma/Wendy London | 2020-08-31 | 2020-08-19 | 2020-08-31 | Complete | 8/31/20: Purpose is confirmed to have access worldwide.
4 | Action | Is there a non-profit cost to R shiny? | NM Team | 2020-08-31 | 2020-08-19 | 2020-08-31 | Complete | 8/31/20: No longer applicable. We will be using a free account.
5 | Action | Provide NM team with information on BCH server so NM team can effectively research pros and cons | Clement Ma/Wendy London | 2020-08-31 | 2020-08-19 | 2020-08-31 | Complete | 8/31/20: No longer needed. We are going with develop on shinyapps.io with the eventual move to AWS.
6 | Action | Explore if Boston has an IT standard on what they put on the cloud vs what they put on the host? | Clement Ma/Wendy London | 2020-08-31 | 2020-08-19 | 2020-08-31 | Complete | 8/31/20: Preference is to include on cloud and development can be done independent on this decision.
7 | Action | Wendy and Clement to find IT person to join next meeting | Clement Ma/Wendy London | 2020-08-31 | 2020-08-19 | 2020-08-31 | Complete | 8/31/20: If we have questions for hosting, Jim Abrahms (BCH) is available. Clement will bring him in when needed.
8 | Action | Follow up on if the proposed R shiny interface mentioned in Technical document is feasible or not feasible or any suggestions on how we can make it better | NM Team | 2020-09-30 | 2020-08-19 | 2020-09-30
9 | Action | Provide BCH with pros and cons of cloud hosting it with shiny vs. hosting the app on BCH’s server. | NM Team | 2020-08-31 | 2020-08-19 | 2020-08-31 | Complete | 8/31/20: No longer needed. We are going with develop on shinyapps.io with the eventual move to AWS.
10 | Action | Need to determine what our deliverables will be to BCH. App, spec document and transition doc. Anything else. | NM Team | 2020-09-15 | 2020-08-19 | 2020-09-15
11 | Action | Share learnings of r shiny capabilities with NM team and BCH to determine if there additional things to incorporate in the app. | NM Team | 2020-09-30 | 2020-08-19 | 2020-09-30
12 | Action | Determine who is respsonsibile for authoring the agreed upon deliverables. | NM Team | 2020-09-15 | 2020-08-19 | 2020-09-15 | Complete | 9/21/20: Stan will document business rules and partner with Danielle for a spec document to be delivered to BCH.
13 | Action | What security concerns/access issues will we potentially run into with a shared github or rshinyapps.io with BCH? What is NM allowed to do? | Judy Berdan | 2020-09-11 | 2020-08-31 | 2020-09-11 | In progress | Can a generic github be possible or should BCH create an account? Will there be firewall or access issues at NM to access this account? What issues will we run into for sharing data/code between BCH/NM?
14 | Action | Create an R shiny account that can be used by all members of the team. | Clement Ma/Wendy London | 2020-09-21 | 2020-09-01 | 2020-09-21
15 | Action | Briefly demo the R code showing the inputs and outputs to understand the business process. | Clement Ma/Wendy London | 2020-09-21 | 2020-09-01 | 2020-09-21
16 | Action | What should our demo cadence be to show Clement and Wendy our work? | NM Team | 2020-09-21 | 2020-09-01 | 2020-09-21
17 | Action | Schedule future meetings with NM Tiger Team. | Lori Kiraly | 2020-09-02 | 2020-08-31 | 2020-09-02 | Complete | 8/31/20: Meetings scheduled through 12/31/20.
18 | Action | Will provide two additional designs to help allow the user to select a different number of designs. | Clement Ma | 2020-12-14 | 2020-11-24 | 2020-12-14
19 | Action | Investigate if the code needs to be changed to have a mean added to the patient allocation plot. | Clement Ma | 2020-12-14 | 2020-11-24 | 2020-12-14
20 | Action | Confirm new plot type for the study duration plot. | Clement Ma | 2020-12-14 | 2020-11-24 | 2020-12-14
21 | Action | Perform user experience testing to provide additional app feedback. The app is located in Ben’s GitHub account. | Clement Ma | 2020-12-14 | 2020-11-24 | 2020-12-14
22 | Action | Investigate different visual options to have the true MTD stand out. | NM Team | 2020-12-14 | 2020-11-24 | 2020-12-14 | In progress
23 | Action | Investigate and development how the user should be able to enter dose level labs alphabetically, alphabetically and numerical or numerical. | NM Team | 2020-12-14 | 2020-11-24 | 2020-12-14
24 | Action | Modify code to have the same dose level labels should appear in the plots. Both the inputs/outputs should have labels. | NM Team | 2020-12-14 | 2020-11-24 | 2020-12-14
25 | Action | Investigate a way to be able to run multiple designs and graphically side by side comparison. | NM Team | 2020-12-14 | 2020-11-24 | 2020-12-14 | Complete
26 | Action | Modify the Patient Allocation Plot to display as a 2x2 grid and include how many patients were allocated. | NM Team | 2020-12-14 | 2020-11-24 | 2020-12-14 | Complete
27 | Action | Modify code to have the plots larger font size and different colors. The colors will be determined. Include the option to make the plot popup and bigger size. | NM Team | 2020-12-14 | 2020-11-24 | 2020-12-14 | Complete
28 | Action | Modify code to shrink size between the inputs and the plots so the plots are larger. | NM Team | 2020-12-14 | 2020-11-24 | 2020-12-14 | Complete
29 | Action | Determine how to have the figures not dynamically change until the simulate button is clicked. | NM Team | 2020-12-14 | 2020-11-24 | 2020-12-14 | Complete
30 | Action | Create document to share with the security team on what we are doing. | Lori Kiraly | 2020-12-14 | 2020-11-24 | 2020-12-14
31 | Action | Setup personal environment. | Lori Kiraly | 2020-11-30 | 2020-11-24 | 2020-11-30
32 | Action | Come up with suggestions on who should appear in the home/help screen. | Stan Crane/Susan Stegman | 2020-12-14 | 2020-11-24 | 2020-12-14
33 | Action | Investigate how to tool tips. | Lori Kiraly | 2020-12-14 | 2020-11-24 | 2020-12-14
34 | Action | Determinue how to document and change business requirements. | Stan | 2020-01-22 | 2020-12-18 | 2020-01-22
35 | Action | Think about and provide different ways that clinicals could break the system that NM could make the coding changes accordingly. | Clement | 2020-01-22 | 2020-12-18 | 2020-01-22
36 | Action | Investigate and provide an understanding to Clement/Wendy on how easy is it to implement changes and hard to implement. | NM Team | 2020-01-22 | 2020-12-18 | 2020-01-22
37 | Action | Review project timeline with foundation leadership and team. | Judy Berdan | 2021-01-29 | 2021-01-12 | 2021-01-29
38 | Action | Review project timeline with Clement and Wendy. | Lori Kiraly | 2021-01-19 | 2021-01-08 | 2021-01-19
39 | Action | Create business rules document to review with NM team and Clement and Wendy. | Lori Kiraly | 2021-01-31 | 2021-01-12 | 2021-01-31
40 | Action | How do we integrate code and scalable from other external clinicals? How does that proces work?
41 | Action | BCH promotion and communication plan. Identify test group of researchers to provide feedback. Should we have potentially joint press release.
42 | Action | BCH has to create a shiny app/github and then need to publish - pre-implementation activities
43 | Action | Determine which NM website should our logo point to (the foundation or the corporate page) | Judy Berdan | 2021-05-14 | 2021-05-04 | 2021-05-14
44 | Action | Provide design user feedback | Nan Jamel/Laure Borchardt | 2021-05-10 | 2021-05-04 | 2021-05-10
45 | Action | Provide updated home page picture showing a diverse adult cancer patient with a headscarf. | Nan Jamel/Laure Borchardt | 2021-05-18 | 2021-04-01 | 2021-05-18
46 | Action | Complete the home tab development. | Stan Crane | 2021-05-14 | 2021-03-01 | 2021-05-14
47 | Action | Complete the about tab development. | Lori Kiraly | 2021-05-14 | 2021-03-01 | 2021-05-14
48 | Action | Complete the help tab development. | Stan Crane | 2021-05-14 | 2021-03-01 | 2021-05-14
49 | Action | Determine how to send all the files to BCH once the project has been transitioned. | Lori Kiraly | 2021-10-15 | 2021-07-15 | 2021-10-15
50 | Action | Wendy will review and make any additional changes. | Wendy London | 2021-08-19 | 2021-08-05 | 2021-08-19
51 | Action | Nan can add the website branding and provide an outlook template to use. | Nan Jamel | 2021-09-02 | 2021-08-19 | 2021-09-02
52 | Action | Judy/Clement will determine if we need to engage another team at NM or the BCH communication team. | Judy Berdan/Clement Ma | 2021-09-02 | 2021-08-19 | 2021-09-02
53 | Action | Nan will provide a higher resolution picture that we selected at the last meeting for the home tab. | Nan Jamel | 2021-08-12 | 2021-08-05 | 2021-08-12
54 | Action
55 | Action
56 | Action
57 | Action
58 | Action
59 | Action
60 | Action
61 | Action
62 | Action
63 | Action
64 | Action
65 | Action
66 | Action
67 | Action
68 | Action
69 | Action
70 | Action
71 | Action
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134

## New Actions after Deployment
New Items after Deployment
Item # | Requester | Request Name | Request Description | Date Identified | Comments | Date Completed | Priority H/M/L